## Sheet1
Date | Activities | Sub-Activities | Venue | Participants | Major Decision Made | Remarks
2022-12-20 | Allocation letter received | GF sent an email with an allocation letter 2023-2025 dated 19 Dec 2022 addressing to CCM Nepal Chair
2023-01-05 | Extended Executive Committee Meeting |  | Kathmandu | Ex-Com and Invitee Members including WHO representative, Directors and Senior Officials from NCASC, NTCC and EDCD, USAID representative | 1. The proposed budget spilt was agreed on. CCM Secretariat will coordinate to get the official signature of the Chair (Dr Roshan Pokhrel) and Civil Society representative (Mr Achut Prasad Sitaula) in the document “Program Split: Confirmation or Change for 2023-2025 Allocation Period”. 2. CCM Secretariat will organize a meeting with NTCC, NCASC and EDCD on the 9th (Mon), 10th (Tues) and 11th (Wed) Jan 2023 respectively
2023-01-09 | Meeting on TB Funding Gap Analysis | Discuss on TB Funding Gap Analysis | NTCC | NTCC, TB implementing partners, CCM Secretariat
2023-01-10 | Meeting on gap analysis for implementing the HIV program | Discuss on gap analysis for implementing the HIV program | NCASC | NCASC, technical partner, implementing partner, CCM Secretariat
2023-01-17 | Malaria consultation meeting with stakeholders | Discuss on gap analysis for implementing the Malaria program | EDCD | EDCD, CCM OC Chair, Technical partner
2023-01-18 | Meeting between the GF CT and CCM Secretariat |  | CCM Secretariat Office, Teku | The GF CT, LFA, and CCM Secretariat
2023-01-18 | Meeting between the GF CT and CCM Executive Committee |  | MoHP | The GF CT, Executive Committee, focal person for the GF in ministry and LFA
2023-01-20 | Discussion on GC7 Funding application | Discussion on GC7 Funding application | Hotel Shankar, Lazimpat | The GF CT, MoHP, three diseases entities, CCM Executive Committee, SCI (PR)
2023-01-25 | Extended Executive Committee Meeting | 1. All the CCM Executive Members agreed on the proposed budget spilt 2. It was decided to allocate more budget from HIV, then TB and minimal from Malaria grant for RSSH. 3. The Core task team was formed to lead the overall process of funding application development. The team comprised members from Executive Committee, three disease entities, NPHL and partners | MoHP | Ex-Com and Invitee Members including WHO representative, Directors/Senior Officials from NCASC, NTC, EDCD and NPHL, USAID representative
2023-02-01 | Meeting between CCM members representing PLHIV constituency and CCM Secretariat | Update and discuss on preparation for funding application for NFM4/GC7 | CCM Secretariat Office, Teku | CCM member and alternate member representing PLHIV constituency and CCM Secretariat
2023-02-02 | Meeting between CCM member representing KP and CCM Secretariat | Update and discuss on preparation for funding application for NFM4/GC7 | CCM Secretariat Office, Teku | Sanjay Sharma and CCM Secretariat
2023-02-07 | 1st Core Task Team Meeting | 2. Discuss and agree on the intended RSSH investment in GC7 3. Discussion and finalization of the roadmap for carrying out the funding application development process to Global Fund, NFM4 4. Co-financing tracking for GC6 (Current Cycle) and the commitment letter for GC7 (Upcoming Cycle): Priority of the Global Fund Country Team 5. Proposed date 23 February 2023 for CCM meeting
2023-02-16 | Signed Program Split Confirmation submitted to the Global Fund
2023-02-23 | CCM Meeting |  | Meetign hall of MoHP |  | CCM members unanimously endorsed the establishment of the Core task team, Disease Specific and RSSH task teams Majority of members, through a voice indicated preference for Co-PR; CCM Secretariat and the MoHP indicated that they would be notifying the CCM, by 9 March 2023 on which modality to go for (ie. EOI vs recommendation by majority vote). Most members however indicated preference for the EOI modality.
2023-03-03 | CCM Update on Country Dialogue |  | Virtually | The GF CT and CCM Secretariat
2023-03-09 | 1st HIV task team meeting |  | NCASC | Task team members and other officials from NCASC | Road map was developed
2023-03-15 | 1st TB task team meeting |  | NTCC | Task team members and other officials from NTCC | Road map was developed
2032-03-16 | 1st Malaria task team meeting |  | EDCD | Task team members and other officials from EDCD | Road map was developed
2023-03-17 | Extended Ex-Com Meeting | Discussion on the modality of PR for the Grant Cycle 7 i.e. 1st August 2024 to 31st July 2027 | MOHP | Executive Committee, Diseases entities, LFA, Development Partners
7